## Cerinte Initiale
Nr | Cerintele Clientului
1 | Valorile senzorilor sunt citite la intervale de o secundă
2 | Toate valorile citite trebuie sa fie într-un interval predefinit. Valorile în afara intervalului sunt ignorate.
3 | Cand trei citiri succesive ale unui senzor generează valori în afara intervalului predefinit un led,ce corespunde senzorului respectiv, își schimba culoarea din verde în roșu (se genereaza ERROR).
4 | În funcție de valorile citite se pot genera semnale WARNING sau ALARM.
5 | Cand un semnal WARNING este generat un led își schimba culoarea din verde în roșu.
6 | Un WARNING persista pana cand este achitat de pilot sau dispar condițiile care l-au generat.
7 | După achitare un nou WARNING va fi generat doar dacă a existat cel puțin o citire pentru care nu s-a generat WARNING sau ALARM.
8 | Cand un semnal ALARMĂ este generat un led își schimba culoarea din verde în roșu.
9 | Un ALARM persista pana cand dispar condițiile care l-au generat.
10 | Cantitatea de CO2 este citită cu ajutorul unui senzor.
11 | Cantitatea de CO2 este afișată pe un ecran de tip ceas
12 | Atunci cand cantitatea de CO2 este este mai mare decat 0.1%, un semnal WARNING este generat
13 | Dacă semnalul WARNING este achitat atunci se porneste instalatia de ventilatie.
14 | Atunci cand cantitatea de CO2 este este mai mare decat 0.3%, un semnal ALARMĂ este generat
15 | După apariția semnalului ALARM se porneste instalatia de ventilatie
16 | Instalatia de ventilatie se oprește dacă cantitatea de CO2 este mai mica decat 0.05%

## Schema SW
System. Req. | SW. Reg. |  | Project Configurations
1 | The System must contain a method that offer an exact time base for the system to work properly.
| 1.1 | A timer isr shall be initialized with a frequency of <project>. | <1 Hz>
| 1.2 | The configured timer ISR shall keep traking of the current time by incrementing a time frame variable.
| 1.3 | All functionality that it not critical shall use the time frame variable.
| 1.4 | Time Critical functionality shall be executed inside ISR thread with the highest priority
2 | The System must check all sensor values and act acordingly.
| 2.1 | Sensor values shall be readed at every <project>. | <1 second>
| 2.2 | The sensor integrity values are between range <project>. | <200 to 1000>
| 2.3 | An number of <project> sensor erounus values shall generate an sensor integrity error. | <3 errors>
3 | The System must have the capability to indicate issues
| 3.1 | When a sensor fault it's detected an ALARM it's rised <project> | <changeing the LED from green to red>
| 3.2 | When CO2 excede <project> an WARNING it's rised <project> | <0.1%><changeing the LED from green to red>
| 3.3 | When CO2 excede <project> an ALARM it's rised <project> | <0.3%><changeing the LED from green to red>
| 3.4 | An issue indicator shall keep it's value untill a value outside risk it's received.
4 | The System shall have a method to clear the issues indicated.
| 4.1 | When an WARNING signal it's confirmed the ventilation shall start automatically
| 4.2 | When an ALARM signal it's generated the ventilation shall start automatically.
| 4.3 | Ventilation shall stop when the issue indicator it's cleared.
5 | The System must offer a method to vizualize the current CO2 concentration.
| 5.1 | The CO2 concentration value shall be displayed at every sensor data received.

## Scheme HW
Tipul Componentei | Componente | Pret | Schema HW
Placa de dezvoltare | Arduino Nano R3 | 22
Senzor CO2 | CO2 sensor Adafruit SGP30 | 19
Led RGB | LED RGB cu Catod Comun | 0.5
Ventilator | DIGIFLEX 120mm Fan | 4
LCD | 16X2 LCD Display with l2C | 4
Alimentare | PEAKTECH sursa de alimentare cu un singur canal | 100
| Total: | 149.5

## Project_Resources
4 week project resource calculator (planned)
| Start Date: | 2021-12-18
|  | week 1 | [6 empty] | week 2 | [6 empty] | week 3 | [6 empty] | week 4 | [6 empty] | Hours: | Cost:
|  | dec | [6 empty] | dec | [6 empty] | jan | [6 empty] | jan
|  | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri
Resource type | Resource name | 2021-12-18 | 2021-12-19 | 2021-12-20 | 2021-12-21 | 2021-12-22 | 2021-12-23 | 2021-12-24 | 2021-12-25 | 2021-12-26 | 2021-12-27 | 2021-12-28 | 2021-12-29 | 2021-12-30 | 2021-12-31 | 2022-01-01 | 2022-01-02 | 2022-01-03 | 2022-01-04 | 2022-01-05 | 2022-01-06 | 2022-01-07 | 2022-01-08 | 2022-01-09 | 2022-01-10 | 2022-01-11 | 2022-01-12 | 2022-01-13 | 2022-01-14
4.14 | Bacanu Alexandra | 2022-01-04: 8; 2022-01-05: 8; 2022-01-06: 8; 2022-01-07: 8; 2022-01-10: 8 | 40 | 165.6
4.2 | Gavrilescu Dragos |  |  | 2 | 2 | 2 | 2 | 4 |  |  | 2 | 2 | 2 | 4 |  |  |  | 2 | 2 | 2 | 2 | 4 |  |  | 2 | 2 | 2 | 2 | 4 | 46 | 193.2
3.92 | Vaduva Mihnea | 2021-12-20: 8; 2021-12-21: 8; 2021-12-28: 8; 2021-12-29: 8; 2021-12-30: 8 | 40 | 156.8
3.83 | Dragan Alin | 2021-12-27: 8; 2021-12-28: 8; 2022-01-03: 8; 2022-01-04: 8; 2022-01-05: 8; 2022-01-06: 8; 2022-01-07: 6 | 54 | 206.82
|  | 2022-01-11: Total Planned Project Hours: | 180
|  | 2022-01-11: Total Planned Project Costs: |  | 722.42
4 week project resource calculator (actual)
| Start Date: | 2021-12-18: 2021-12-18
|  | 2021-12-18: week 1; 2021-12-25: week 2; 2022-01-01: week 3; 2022-01-08: week 4 | Hours: | Cost:
|  | dec | [6 empty] | dec | [6 empty] | jan | [6 empty] | jan
|  | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri
Resource type | Resource name | 2021-12-18 | 2021-12-19 | 2021-12-20 | 2021-12-21 | 2021-12-22 | 2021-12-23 | 2021-12-24 | 2021-12-25 | 2021-12-26 | 2021-12-27 | 2021-12-28 | 2021-12-29 | 2021-12-30 | 2021-12-31 | 2022-01-01 | 2022-01-02 | 2022-01-03 | 2022-01-04 | 2022-01-05 | 2022-01-06 | 2022-01-07 | 2022-01-08 | 2022-01-09 | 2022-01-10 | 2022-01-11 | 2022-01-12 | 2022-01-13 | 2022-01-14
4.14 | Bacanu Alexandra | 2022-01-04: 8; 2022-01-05: 6; 2022-01-06: 8; 2022-01-07: 6; 2022-01-10: 8 | 36 | 149.04
4.2 | Gavrilescu Dragos |  |  | 2 | 2 | 2 |  | 4 |  |  | 2 | 2 | 2 | 4 |  |  |  |  | 2 | 2 | 2 | 4 |  |  | 2 | 2 | 2 | 2 | 4 | 42 | 176.4
3.92 | Vaduva Mihnea | 2021-12-20: 8; 2021-12-21: 8; 2021-12-28: 6; 2021-12-29: 8; 2021-12-30: 8 | 38 | 148.96
3.83 | Dragan Alin | 2021-12-27: 8; 2021-12-28: 8; 2022-01-03: 8; 2022-01-04: 8; 2022-01-05: 6; 2022-01-06: 8; 2022-01-07: 6 | 52 | 199.16
|  | 2022-01-11: Total Actual Project Hours: | 168
|  | 2022-01-11: Total Actual Project Costs: |  | 673.56